## Sheet1
Tasks | Staff Assigned | Time Allocated (hours) | Time Allocated (Days) | Start Date | End Date | 2024-04-19 |  |  |  |  | 2024-04-24 |  |  |  |  | 2024-04-29 |  |  |  |  | 2024-05-04 |  |  |  |  | 2024-05-09 |  |  |  |  | 2024-05-14 |  |  |  |  | 2024-05-19 |  |  |  |  | 2024-05-24
Installing Hardware and Laying Infrastructure |  | 248 | 31 | 2024-04-19 | 2024-05-01 | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Upgrade resturant infrastructure | Shura Khan | 105 | 13.13 | 2024-04-19 | 2024-05-02 03:07 | bar: 2024-04-19 M to 2024-04-29 T
Deploy and configure cloud server | Shura Khan | 25 | 3.13 | 2024-05-02 03:07 | 2024-05-05 06:14 | bar: 2024-04-29 T to 2024-05-04 T
Installation of hardware | Shura Khan | 70 | 8.75 | 2024-05-05 06:14 | 2024-05-14 00:14 | bar: 2024-05-04 T to 2024-05-04 W
Testing of Hardware | Shura Khan | 48 | 6 | 2024-05-14 00:14 | 2024-05-20 00:14 | bar: 2024-05-04 W to 2024-05-09 T
Module 1: Back-end Database |  | 75 | 9.38 | 2024-05-13 | 2024-05-22
Develop | Heather Holt | 40 | 5 | 2024-05-13 | 2024-05-18
Deploy | Heather Holt | 9 | 1.13 | 2024-05-18 | 2024-05-19 03:07
Unit Testing | Heather Holt | 20 | 2.5 | 2024-05-19 03:07 | 2024-05-21 15:07
Fixing and regression for minor fault | Heather Holt | 6 | 0.75 | 2024-05-21 15:07 | 2024-05-22 09:07
Module 2: Stock control and Inventory Management |  | 80 | 10 | 2024-05-13 | 2024-05-23
Develop | Iwan Jones | 40 | 5 | 2024-05-13 | 2024-05-18
Deploy | Iwan Jones | 20 | 2.5 | 2024-05-18 | 2024-05-20 12:00
Unit Testing | Iwan Jones | 13 | 1.63 | 2024-05-20 12:00 | 2024-05-22 03:07
Fixing and regression for minor fault | Iwan Jones | 7 | 0.88 | 2024-05-22 03:07 | 2024-05-23 00:14
Module 3: Table management - orders and billing |  | 55 | 6.88 | 2024-05-13 | 2024-05-19
Develop | Viktor Alvarado | 25 | 3.13 | 2024-05-13 | 2024-05-16 03:07
Deploy | Viktor Alvarado | 16 | 2 | 2024-05-16 03:07 | 2024-05-18 03:07
Unit Testing | Viktor Alvarado | 9 | 1.13 | 2024-05-18 03:07 | 2024-05-19 06:14
Fixing and regression for minor fault | Viktor Alvarado | 5 | 0.63 | 2024-05-19 06:14 | 2024-05-19 21:22
Module 4: User interface |  | 50 | 6.25 | 2024-05-13
Develop | Stephanie Hammond |  | 0 | 2024-05-13 | 2024-05-13
Deploy | Stephanie Hammond |  | 0 | 2024-05-13 | 2024-05-13
Unit Testing | Stephanie Hammond |  | 0 | 2024-05-13 | 2024-05-13
Fixing and regression for minor fault | Stephanie Hammond |  | 0 | 2024-05-13 | 2024-05-13
Module 5: Data analysis |  | 95 | 11.88
Develop | Heather Holt |  | 0
Deploy | Heather Holt |  | 0
Unit Testing | Heather Holt |  | 0
Fixing and regression for minor fault | Heather Holt |  | 0
Module 6: Customer online booking portal |  | 100 | 12.5 | bar: 2024-04-19 T to 2024-04-24 T
Develop | Iwan Jones |  | 0 | bar: 2024-04-24 T to 2024-04-24 W
Deploy | Iwan Jones |  | 0 | bar: 2024-04-24 W to 2024-04-24 F
Unit Testing | Stephanie Hammond |  | 0 | bar: 2024-04-24 F to 2024-04-29 M
Fixing and regression for minor fault | Viktor Alvarado
Training, faluts and testing
Training resturant staff | bar: 2024-04-19 T to 2024-04-24 T